## Durations
Activity | Very Small < 150 m2 | Small 150-500 m2 | Medium 500-2000 m2 | Large > 2000 m2 | Unit | Notes
PRE-DESIGN SURVEYS
Asbestos — Management | 0 – 1 | 1 – 2 | 2 – 3 | 2 – 3 | wks | Pre-2000 building, no demolition/structural alterations.
Asbestos — R&D Survey | 1 – 2 | 2 – 3 | 2 – 3 | 3 – 4 | wks | Pre-1980 OR demolition/structural alterations OR asbestos known.
Structural Survey | 1 – 1 | 1 – 2 | 2 – 3 | 2 – 3 | wks | Structural concerns (Q3.1) or structural alterations in scope (Q2.2).
Condition Survey | 1 – 1 | 1 – 2 | 1 – 2 | 2 – 3 | wks | Refurbishment only. Parallel with other surveys.
Topographic Survey | 1 – 1 | 1 – 2 | 1 – 2 | 2 – 3 | wks | New build and extension always. Parallel with other surveys.
Ground Investigation | 3 – 6 | 3 – 6 | 3 – 6 | 3 – 6 | wks | New build / extension / contaminated land. Parallel with other surveys.
RIBA DESIGN STAGES
Stage 2 — Concept Design | 1 – 2 | 3 – 4 | 6 – 8 | 8 – 10 | wks | Multiply by Q2.3 design duration multiplier. Add uplifts below if triggered.
Stage 2 Uplift — Structural | + 1 | + 2 | + 2 | + 3 | wks | Add when structural alterations in scope. Not scaled by Q2.3 multiplier.
Stage 2 Uplift — Listed Building | + 2 | + 3 | + 4 | + 4 | wks | Add when Pre-1900 building. Heritage consultant required.
Stage 3 — Developed Design | 2 – 3 | 4 – 6 | 6 – 8 | 8 – 12 | wks | Apply Q2.3 multiplier. Planning application submitted at start of Stage 3.
Stage 3 Uplift — M&E Heavy | + 1 | + 2 | + 2 | + 3 | wks | Add when 4+ M&E systems in scope.
Stage 3 Uplift — Specialist | + 1 | + 2 | + 2 | + 3 | wks | Add when labs, clinical rooms, or data centres in scope.
Stage 4 — Technical Design | 2 – 3 | 4 – 7 | 6 – 8 | 8 – 12 | wks | Apply Q2.3 multiplier. Building control Full Plans submitted here.
Stage 4 Uplift — M&E / Specialist | + 1 | + 2 | + 3 | + 4 | wks | Add when M&E-heavy or specialist project.
CLIENT GATEWAYS
Client Gateway | 1 | 2 | 2 | 2 | wks | Applied after each of Stages 3, and 4. Very Small = 1 wk; all others = 2 wks.
PLANNING CONSENTS
Planning — Full Permission | 8 – 13 | 8 – 13 | 8 – 13 | 8 – 13 | wks | Statutory determination. Runs in parallel with Stage 3.
Planning — Listed Building Consent | 8 – 13 | 8 – 13 | 8 – 13 | 8 – 13 | wks | Dual consent risk — flag HIGH risk if sequential to full planning.
Planning — Prior Approval | 4 – 8 | 4 – 8 | 4 – 8 | 4 – 8 | wks | Shorter statutory period. Place at start of Stage 3.
Planning — Change of Use | 8 – 13 | 8 – 13 | 8 – 13 | 8 – 13 | wks | Same statutory period as full planning.
Planning — Pre-Application | 4 – 6 | 4 – 6 | 4 – 6 | 4 – 6 | wks | Add when unsure of consent type. Place at end of Stage 2.
BUILDING CONTROL
Building Control — LABC | 2 – 4 | 2 – 4 | 5 – 8 | 5 – 8 | wks | Standard route. Parallel with Stage 4. RBCA is faster option if programme critical.
Building Control — RBCA | 3 – 5 | 3 – 5 | 3 – 5 | 3 – 5 | wks | Programme-critical projects only. Decision by PM at Stage 2.
TENDER / PROCUREMENT
Tender — Formal Competitive | 10 – 12 | 10 – 12 | 10 – 12 | 10 – 12 | wks | Works cost over £100,000. Full ITT process, evaluation, and contract award.
Tender — 3 Quotations | 3 – 4 | 4 – 6 | 4 – 6 | 4 – 6 | wks | Works cost under £100,000. Very Small = 3-4 wks; all others = 4-6 wks.

## Construction
Project Type | Very Small < 150 m2 | Up to 250 m2 | 250-500 m2 | 500-1500 m2 | 1500-3000 m2 | Unit | Notes / AI Selection Logic
New Build — Standard | 14 – 18 | 16 – 22 | 22 – 34 | 30 – 48 | 44 – 64 | wks | Offices, education, student accommodation, general commercial. Apply when building use is not healthcare, industrial, or specialist.
New Build — Healthcare / Specialist | 18 – 24 | 22 – 32 | 32 – 48 | 44 – 64 | 60 – 84 | wks | Hospitals, clinical, lab-heavy facilities. High M&E content, commissioning and validation. Apply when building use is Healthcare.
New Build — Industrial / Warehouse | 6 – 10 | 8 – 14 | 14 – 22 | 22 – 36 | 32 – 52 | wks | Steel portal frame, minimal fit-out. Apply when building use is Industrial / warehouse.
Extension — Single Storey | 7 – 10 | 8 – 12 | 12 – 18 | 18 – 26 | — | wks | Groundworks, frame, envelope, fit-out in sequence.
Extension — Multi-Storey | 10 – 14 | 12 – 18 | 18 – 26 | 26 – 40 | 36 – 52 | wks | Steel or RC frame, multiple floor fits. Steelwork lead time 8-12 weeks.
Refurb — M&E Replacement | 4 – 7 | 5 – 8 | 8 – 14 | 14 – 22 | 22 – 36 | wks | Full or partial services replacement. Phased shutdowns for occupied buildings. Always the longest refurb row — used when 3+ M&E systems in scope.
Refurb — Fabric / Envelope | 3 – 5 | 4 – 6 | 6 – 10 | 10 – 18 | 18 – 28 | wks | Roof, facade, windows, waterproofing. Weather dependency adds risk. Apply when M&E is not primary scope.
Fit-Out — Cat B / High Spec | 4 – 6 | 5 – 8 | 8 – 12 | 12 – 20 | 20 – 32 | wks | Bespoke joinery, feature ceilings, specialist finishes. Apply when spec level = High.
Fit-Out — Basic / Cat A | 3 – 5 | 4 – 6 | 6 – 10 | 10 – 16 | 16 – 26 | wks | Standard offices, general academic. Partitions, ceiling, floor, M&E 1st and 2nd fix.
Specialist — Labs / Healthcare | 6 – 10 | 8 – 12 | 12 – 18 | 18 – 28 | 28 – 44 | wks | High M&E content, commissioning and validation. Labs, clinical, data centres. Apply regardless of project type when specialist rooms in scope.
External Works | 2 – 3 | 2 – 4 | 4 – 6 | 6 – 10 | 10 – 16 | wks | Landscaping, car park, drainage, paths. Winter start adds 2-4 weeks.
Demolition / Enabling | 1 – 2 | 2 – 3 | 3 – 5 | 4 – 8 | 6 – 12 | wks | Asbestos removal adds 1-4 weeks. Structural demolition requires propping.
Handover | 1 – 2 | 2 – 4 | 2 – 4 | 3 – 6 | 4 – 8 | wks | Commissioning, snagging, Practical Completion sign-off.

## Assumptions
Code | Assumption Text
A1 | Programme durations are indicative only and based on information provided at RIBA Stage 0-1. Actual durations to be confirmed at Stage 2 once surveys, design scope, and procurement strategy are finalised.
A2 | Durations assume client decision-making within the gateway periods shown. Delays to client sign-off will extend the programme accordingly.
A3 | Planning determination periods are based on statutory LPA timescales. No allowance has been made for objections, committee referral, or appeals.
A4 | Building control approval: LABC Full Plans route assumed (5-8 weeks), running in parallel with Stage 4. A private RBCA (3-5 weeks) should be considered for programme-critical projects — decision to be confirmed by the PM at Stage 2.
A5 | Construction duration is benchmarked against project size and type at standard productivity rates. Actual duration to be confirmed at Stage 2 by the appointed contractor or QS.
A6 | Where the building is occupied during works, a programme uplift has been applied for access management, phasing, noise and dust control, and increased supervision requirements.
A7 | Surveys identified as required but not yet commissioned are shown at the start of Stage 2. Commissioning and completing surveys before Stage 2 design commences will be a gateway condition.
A8 | The programme does not show calendar dates. Durations are shown as weeks from a notional project start (Week 0 = Gateway 1 approval).
A9 | Procurement threshold applied: formal competitive tender (10-12 weeks) for works over £100,000; three quotations (4-6 weeks) for works under £100,000.
A10 | Handover (RIBA Stage 6) includes commissioning, snagging, and Practical Completion sign-off. The defects liability period begins at Practical Completion and is typically 12 months.