## Design Stage Durations
ESTATES AI TOOL ¦ Programme Duration Reference — Design Stages
Version 1.0 ¦ May 2026 ¦ Prepared by Nabil Kayali ¦ All durations in weeks
RIBA Stage / Activity | Small < 500 m² | Medium 500 – 2,000 m² | Large > 2,000 m² | Unit | Notes & AI Selection Logic
PRE-DESIGN ACTIVITIES
Asbestos Survey — Management | 1 – 2 | 2 – 3 | 2 – 3 | wks | Apply when building pre-1980 (Q1.4). Management survey for occupied buildings. Placed at start of Stage 2.
Asbestos Survey — Refurb / Demolition | 2 – 3 | 2 – 3 | 3 – 4 | wks | Apply when demolition or structural alterations in scope (Q2.2), or asbestos known/suspected (Q3.4). Higher risk = upper end.
Structural Survey | 1 – 2 | 2 – 3 | 2 – 3 | wks | Apply when structural concerns (Q3.4) or structural alterations in Q2.2. Place at start of Stage 2.
Condition Survey | 1 – 2 | 1 – 2 | 2 – 3 | wks | Apply for refurbishment projects where existing building condition is not documented. Place at start of Stage 2.
Topographic / Measured Building Survey | 1 – 2 | 1 – 2 | 2 – 3 | wks | Apply when no existing measured drawings available. Always apply for new build and extension projects.
Ground Investigation | 3 – 4 | 3 – 5 | 4 – 6 | wks | Apply for new build (Q1.2), extension with new foundations, or contaminated land (Q3.4). Desktop study first (1 wk), intrusive investigation second.
RIBA DESIGN STAGES — Indicative Durations (Client Decision Gateway: +2 weeks after each stage)
Stage 2 — Concept Design (includes surveys at start) | 6 – 8 | 8 – 12 | 12 – 18 | wks | Start of design. Architectural concept, initial M&E strategy, cost plan. Surveys run in parallel at start.
Stage 2 Uplift — Structural Alterations | + 2 | + 2 | + 3 | wks | Add when structural alterations or openings in Q2.2. Structural engineer required for concept-stage input.
Stage 2 Uplift — Listed Building / Pre-1900 | + 3 | + 4 | + 4 | wks | Add when Q1.4 = Pre-1900 or listed building likely. Heritage consultant input and BREEAM/heritage strategy required.
Stage 3 — Developed Design (planning application runs here) | 5 – 7 | 7 – 11 | 10 – 14 | wks | Spatial coordination, structural scheme, M&E coordination. Planning application submitted at start of Stage 3.
Stage 3 Uplift — M&E-Heavy Scope | + 2 | + 2 | + 3 | wks | Add when M&E-heavy scope (labs, healthcare, full M&E replacement). Additional engineering coordination required.
Stage 3 Uplift — Specialist Fit-Out | + 2 | + 2 | + 3 | wks | Add when specialist rooms (labs, theatres, data rooms) in Q2.2. Specialist consultant required for room data sheets.
Stage 4 — Technical Design (building control submission) | 5 – 8 | 8 – 13 | 12 – 20 | wks | Full construction information. Building control Full Plans submitted here. Procurement package prepared.
Stage 4 Uplift — Complex M&E / Specialist | + 2 | + 3 | + 4 | wks | Add for M&E-heavy or specialist projects where detailed system design and coordination takes longer.
Client Gateway — after each stage (2 weeks — built in separately) | 2 | 2 | 2 | wks | Fixed 2-week client review and sign-off period after each stage submission. Apply after Stage 2, 3, and 4.

## Regulatory & Procurement
ESTATES AI TOOL ¦ Programme Duration Reference — Regulatory & Procurement Periods
Version 1.0 ¦ May 2026 ¦ All durations in weeks ¦ Apply sequentially unless noted as parallel
Activity / Consent Type | Minimum Duration | Maximum Duration | Unit | AI Selection Logic & Programme Placement
PLANNING CONSENTS — Stage 3 (run in parallel with Developed Design where possible)
Full Planning Permission | 8 | 13 | wks | Statutory determination period. Submit at start of Stage 3. Does NOT add sequentially if run in parallel with Stage 3 design — flag as risk if Stage 3 duration is shorter than planning period.
Listed Building Consent (LBC) | 8 | 13 | wks | Run alongside full planning where possible. Dual-consent risk: if LBC determination is sequential to planning, add 8–13 weeks. Flag explicitly as HIGH risk in programme.
Prior Approval | 4 | 8 | wks | Apply when Q3.5 = Prior approval. Shorter period, typically residential/PD extensions. Place at start of Stage 3.
Change of Use Consent | 8 | 13 | wks | Apply when Q2.3 = Modification with change of use or when Q3.5 flags change of use. Same statutory period as full planning.
Permitted Development — No Consent | 0 | 0 | wks | No programme allowance needed. Confirm PD applies via pre-application check if unsure.
Pre-Application Advice (where required) | 4 | 6 | wks | Add when Q3.5 = Unsure or Q1.4 = Pre-1900. Pre-app advice before formal submission. Place at end of Stage 2.
BUILDING CONTROL — Stage 3/4 boundary (Full Plans route recommended for all commercial / estates projects)
Building Control — Local Authority (LABC) Full Plans Submission | 5 | 8 | wks | Statutory: 5 weeks or 2 months with consent. Allow 6–8 weeks in programme for commercial projects. Place at Stage 3/4 boundary. Inspections then continue throughout Stage 5 — no additional programme time.
Building Control — Private RBCA (Registered Building Control Approver) | 3 | 5 | wks | Faster and more flexible. Recommended for programme-critical projects. Allow 3–5 weeks. Same Full Plans route — Initial Notice submitted to LA. Lower end if early engagement with RBCA during Stage 3.
Higher Risk Buildings (HRB) — BSR Route (7+ storeys or complex mixed use) | 26 | 36 | wks | Building Safety Regulator (BSR) route for HRBs only. 2025 average: 36 weeks. Flag as CRITICAL PROGRAMME RISK if project is HRB. Must be identified at Stage 1.
PROCUREMENT & TENDER PERIODS — Threshold Rule: Over £100k = Formal Competitive Tender ¦ Under £100k = 3 Quotations
Formal Competitive Tender (Construction budget OVER £100,000) | 10 | 12 | wks | Apply when cost estimate mid-point exceeds £100k. Full ITT/ITP process required. Placed at Stage 4/5 boundary. Includes tender period + evaluation + contract award.
3 Quotations — Direct Approach (Construction budget UNDER £100,000) | 4 | 6 | wks | Apply when cost estimate mid-point is under £100k. Shorter quotation period acceptable. Allow 4–6 weeks including evaluation and award.
Design & Build — Employer's Requirements Tender (D&B procurement route) | 10 | 12 | wks | Apply when D&B route selected (Q5.2). Same 10–12 / 4–6 week threshold rule applies. Contractor appointed at end of Stage 2 or 3.
PCSA Period (Pre-Construction Services Agreement) | 8 | 16 | wks | Apply when PCSA route selected. Runs alongside Stage 2–3 design. Show as parallel bar in programme. Main contract awarded at end of PCSA following open-book pricing agreement.
Two-Stage Tender — Stage 1 (Prelims / OH&P selection) | 6 | 8 | wks | First stage: select contractor on overhead and profit. Place at end of Stage 2.
Two-Stage Tender — Stage 2 (Full pricing at Stage 4) | 6 | 8 | wks | Second stage: full price agreed at Stage 4 completion. Both stages shown explicitly in programme.

## Construction Duration
ESTATES AI TOOL ¦ Programme Duration Reference — Construction Duration Benchmarks
Version 1.0 ¦ May 2026 ¦ Durations in weeks ¦ Based on RIBA Stage 5 only (excludes handover)
Project Type | Up to 250 m² | 250 – 500 m² | 500 – 1,500 m² | 1,500 – 3,000 m² | Unit | Complexity Uplifts & AI Selection Logic
PROJECT TYPE — CONSTRUCTION DURATIONS (RIBA Stage 5)
Internal Fit-Out — Basic / Cat A (offices, general academic space) | 4 – 6 | 6 – 10 | 10 – 16 | 16 – 26 | wks | Cat A: partitions, ceiling, floor, M&E first fix and second fix. Occupied uplift: add 20–30%. Basic = lower end.
Internal Fit-Out — Cat B / High Spec (bespoke finishes, joinery, AV) | 5 – 8 | 8 – 12 | 12 – 20 | 20 – 32 | wks | Bespoke joinery, feature ceilings, specialist finishes extend programme. Cat B always at upper end of range.
Specialist Fit-Out — Labs / Healthcare (M&E-heavy, containment, cleanroom) | 8 – 12 | 12 – 18 | 18 – 28 | 28 – 44 | wks | High M&E content — commissioning and validation extend construction period significantly. Always use upper end.
Refurbishment — Fabric / Envelope (roof, facade, windows, waterproofing) | 4 – 6 | 6 – 10 | 10 – 18 | 18 – 28 | wks | Weather dependency adds risk. Listed buildings at upper end. Winter works may extend further.
Refurbishment — M&E Replacement (full or partial services replacement) | 5 – 8 | 8 – 14 | 14 – 22 | 22 – 36 | wks | Phased shutdowns for live buildings add duration. Fully vacant = lower end. Occupied = upper end + 20–30%.
Extension — Single Storey (structural frame + fit-out) | 8 – 12 | 12 – 18 | 18 – 26 | — | wks | Groundworks + frame + envelope + fit-out in sequence. Brownfield or contaminated ground = add 4–6 weeks.
Extension — Multi-Storey (2+ floors, structural frame) | 12 – 18 | 18 – 26 | 26 – 40 | 36 – 52 | wks | Steel or RC frame + multiple floor fits. Procurement of structural steelwork: allow 8–12 weeks lead time.
New Build — Standard Commercial (office, education, general purpose) | 16 – 22 | 22 – 34 | 30 – 48 | 44 – 64 | wks | Full new build: groundworks, frame, envelope, M&E, fit-out. Larger = always upper end. Seasonal risk applies.
External Works Only (landscaping, car park, drainage, paths) | 2 – 4 | 4 – 6 | 6 – 10 | 10 – 16 | wks | Weather and ground conditions drive duration. Winter start = add 2–4 weeks. Utility diversions = add 4–8 weeks.
Enabling Works / Demolition Only | 2 – 3 | 3 – 5 | 4 – 8 | 6 – 12 | wks | Asbestos removal adds 1–4 weeks depending on volume. Structural demolition requires propping — allow extra.
MANDATORY UPLIFTS — Apply on top of base construction duration above
Occupied During Works — Full occupation throughout | + 25% – 35% | — | — | — | % | Phasing, out-of-hours working, noise & dust management, increased supervision. Use 30% as default mid-point.
Occupied During Works — Partial / phased | + 15% – 25% | — | — | — | % | Section-by-section handover. Use 20% as default. Programme shows phased completion sequence.
Access Restrictions — Term-time only working | + 15% – 20% | — | — | — | % | Works only permitted outside academic term. Effective working weeks reduced significantly. Flag as risk.
Access Restrictions — Restricted hours (e.g. 8am–4pm only, no nights) | + 10% – 15% | — | — | — | % | Lost productivity on multi-trade activities. Plant movements limited. Add 10% minimum.
Handover (RIBA Stage 6) (Commissioning, snagging, PC) | 2 – 4 | 2 – 4 | 3 – 6 | 4 – 8 | wks | Always shown separately after construction. Includes commissioning, snagging, and Practical Completion sign-off.

## AI Selection Logic
ESTATES AI TOOL ¦ Programme Module — AI Selection Logic Reference
This tab summarises how the AI should select durations from the reference tables above. For Claude Code prompt construction.
Decision Point | Questionnaire Input(s) | Programme Action
Which size band to use for design stage and construction durations | Q1.5 — Approximate project size (m²) | < 500 m² = Small. 500–2,000 m² = Medium. > 2,000 m² = Large. Use size band columns from Design Stage Durations and Construction Duration tabs.
When to include Asbestos Survey in programme | Q1.4 (building age), Q3.4 (known building issues), Q2.2 (demolition or structural works ticked) | Pre-1980 building → management survey. Demolition or structural alterations → refurb/demolition survey. Both triggers → use refurb/demolition survey duration (longer). Place at start of Stage 2.
When to include Structural Survey | Q3.4 (structural concerns ticked), Q2.2 (structural alterations ticked) | Either trigger = include structural survey, 2–3 weeks at start of Stage 2.
When to include Ground Investigation | Q1.2 (new build or extension), Q1.3 (brownfield), Q3.4 (contaminated land) | New build or brownfield or contaminated = include ground investigation, 3–6 weeks. Place at Stage 2 start alongside other surveys.
Design stage duration — which end of range | Q2.2 (scope complexity), Q1.4 (building age), Q2.5 (standards), Q3.2 (occupation) | Lower end: simple scope, no structural alterations, vacant building. Upper end: structural alterations, M&E-heavy, listed building, BREEAM/specialist standards, occupied.
Planning consent — which type and duration | Q3.5 (planning consents required), Q1.4 (listed building probability) | Full planning = 8–13 weeks at Stage 3. LBC alongside = dual-consent risk, flag explicitly. Pre-app if unsure = add 4–6 weeks. Permitted development = no allowance.
Building control route — LABC vs private RBCA | Q3.1 (target completion date — programme-critical?), Q1.4 (conservation area risk) | Programme-critical project → recommend private RBCA (3–5 weeks). Standard project → LABC (6–8 weeks). HRB (7+ storeys) → BSR route, flag 26–36 weeks as critical risk.
Procurement — formal tender vs 3 quotations | Cost estimate mid-point (generated by cost module) | Mid-point > £100k → formal competitive tender, 10–12 weeks. Mid-point < £100k → 3 quotations, 4–6 weeks. Place at Stage 4/5 boundary.
Construction duration — which type and size band | Q1.2 (project type), Q1.3 (building use), Q2.2 (scope), Q1.5 (m²) | Match project type to Construction Duration tab row. Apply size band column. Add occupancy uplift from Q3.2. Add access uplift from Q3.3.
Occupancy uplift on construction duration | Q3.2 (occupation during construction) | Fully occupied = +25–35%. Partially occupied = +15–25%. Full decant or vacant = no uplift. Apply to base construction duration.
Target completion date feasibility check | Q3.1 (target completion date) | Sum all stage durations, surveys, regulatory periods, procurement, construction, and handover. Compare total to target. If unreachable → flag as HIGH risk. State minimum realistic end date.
Overall programme summary — one-line output | All questionnaire inputs, all duration selections above | AI outputs: total weeks from project start, broken into: [Pre-Design] + [Stage 2] + [Stage 3 / Planning] + [Stage 4 / BC] + [Tender] + [Construction] + [Handover]. Show as a single bar chart / Gantt with key milestone markers and target end date.

## Programme Assumptions
ESTATES AI TOOL ¦ Standard Programme Assumptions — Include in every report
These assumptions must be included verbatim (or adapted to project) in every programme section of a generated report.
STANDARD ASSUMPTIONS — Populate in every programme section
A1 | Programme durations are indicative only and based on information provided at RIBA Stage 0–1. Actual durations to be confirmed at Stage 2 once surveys, design scope, and procurement strategy are finalised.
A2 | Durations assume client decision-making within 2 weeks of each gateway submission. Delays beyond this will extend the programme accordingly.
A3 | Planning determination periods are based on statutory LPA timescales. No allowance has been made for delays due to information requests, committee referral, objections, or appeals.
A4 | Building control approval durations are indicative and based on [LABC / private RBCA route]. Inspections during construction are not shown as separate programme items — they are assumed to be concurrent with construction activities.
A5 | Construction duration is benchmarked against [X m² of [project type]] at standard productivity rates. Actual duration to be confirmed at Stage 2 by the appointed contractor or QS.
A6 | If the building is occupied during works, a programme uplift of [X%] has been applied for access management, phasing, noise and dust control, and increased supervision requirements.
A7 | Surveys identified as required but not yet commissioned are shown at the start of Stage 2. Commissioning and completing surveys before Stage 2 design commences will be a gateway condition.
A8 | The programme does not show calendar dates as the project start date is not confirmed at Stage 1. Durations are shown as weeks from a notional project start (Week 0 = Gateway 1 approval).
A9 | Procurement threshold rule applied: construction estimate mid-point [above / below] £100,000. [Formal competitive tender 10–12 weeks / 3 quotations 4–6 weeks] applied accordingly.
A10 | Handover (RIBA Stage 6) includes commissioning, snagging, and Practical Completion sign-off. The defects liability period is not shown in the programme — it begins at Practical Completion and is typically 12 months.