## Design Stage Durations
ESTATES AI TOOL ¦ Programme Duration Reference — Design Stages
Version 2.0 ¦ May 2026 ¦ Prepared by Nabil Kayali ¦ All durations in weeks
SINGLE SOURCE OF TRUTH FOR ALL DURATIONS. The app reads weeks from this workbook only — never from the AI. Occupation uplifts here (full 30%, partial 20%) override any other document. Coordinated with NRM1 v3 and Questionnaire v4.
RIBA Stage / Activity
PRE-DESIGN ACTIVITIES
Asbestos Survey — Management | 1 – 2 | 2 – 3 | 2 – 3 | wks | Asbestos RISK is flagged for any pre-2000 building (Q1.4, per CAR 2012). SURVEY TYPE escalates by age: pre-2000 occupied refurb = Management survey (this row). Pre-1980 OR demolition/structural OR asbestos suspected = Refurbishment/Demolition survey (row below). This resolves the pre-2000 vs pre-1980 coordination point.
Asbestos Survey — Refurb / Demolition | 2 – 3 | 2 – 3 | 3 – 4 | wks | Apply when demolition or structural alterations in scope (Q2.2), or asbestos known/suspected (Q3.4). Higher risk = upper end.
Structural Survey | 1 – 2 | 2 – 3 | 2 – 3 | wks | Apply when structural concerns (Q3.4) or structural alterations in Q2.2. Place at start of Stage 2.
Condition Survey | 1 – 2 | 1 – 2 | 2 – 3 | wks | Apply for refurbishment projects where existing building condition is not documented. Place at start of Stage 2.
Topographic / Measured Building Survey | 1 – 2 | 1 – 2 | 2 – 3 | wks | Apply when no existing measured drawings available. Always apply for new build and extension projects.
Ground Investigation
RIBA DESIGN STAGES — Indicative Durations (Client Decision Gateway: +2 weeks after each stage)
Stage 2 — Concept Design (includes surveys at start) | 6 – 8 | 8 – 12 | 12 – 18 | wks | Start of design. Architectural concept, initial M&E strategy, cost plan. Surveys run in parallel at start.
Stage 2 Uplift — Structural Alterations | + 2 | + 2 | + 3 | wks | Add when structural alterations or openings in Q2.2. Structural engineer required for concept-stage input.
Stage 2 Uplift — Listed Building / Pre-1900 | + 3 | + 4 | + 4 | wks | Add when Q1.4 = Pre-1900 or listed building likely. Heritage consultant input and BREEAM/heritage strategy required.
Stage 3 — Developed Design (planning application runs here) | 5 – 7 | 7 – 11 | 10 – 14 | wks | Spatial coordination, structural scheme, M&E coordination. Planning application submitted at start of Stage 3.
Stage 3 Uplift — M&E-Heavy Scope | + 2 | + 2 | + 3 | wks | Add when M&E-heavy scope (labs, healthcare, full M&E replacement). Additional engineering coordination required.
Stage 3 Uplift — Specialist Fit-Out | + 2 | + 2 | + 3 | wks | Add when specialist rooms (labs, theatres, data rooms) in Q2.2. Specialist consultant required for room data sheets.
Stage 4 — Technical Design (building control submission) | 5 – 8 | 8 – 13 | 12 – 20 | wks | Full construction information. Building control Full Plans submitted here. Procurement package prepared.
Stage 4 Uplift — Complex M&E / Specialist | + 2 | + 3 | + 4 | wks | Add for M&E-heavy or specialist projects where detailed system design and coordination takes longer.
Client Gateway — after each stage (2 weeks — built in separately) | 2 | 2 | 2 | wks | Fixed 2-week client review and sign-off period after each stage submission. Apply after Stage 2, 3, and 4.
DESIGN DURATION BY LEVEL OF INTERVENTION (Q2.3) — multiplier applied to the Stage 2–4 design durations above
Q2.3 Level of Intervention | Design Duration Multiplier | Survey Allowance | Notes & AI Selection Logic
Light touch | × 0.7 of base design weeks | Minimal — condition check only | Cosmetic works; limited design coordination. Use lower end of Stage 2–4 ranges.
Full refurbishment | × 1.0 (base design weeks) | Standard survey package | Major systems & finishes; full design coordination. Use mid of Stage 2–4 ranges.
Complete strip-out | × 1.3 of base design weeks | Full surveys (asbestos R&D, structural, M&E) | Gut refurbishment; maximum design + survey coordination. Use upper end + survey weeks.
(New Build / Extension) | × 1.0 (base design weeks) | Ground investigation + topographic | Q2.3 not asked; use base design durations for the size band.
This table links Q2.3 (also used by the NRM1 cost band) to design duration. Same answer drives both cost band and design weeks — no contradiction. Construction durations use the separate Construction Duration tab.

## Regulatory & Procurement
ESTATES AI TOOL ¦ Programme Duration Reference — Regulatory & Procurement Periods
Version 2.0 ¦ May 2026 ¦ All durations in weeks ¦ Apply sequentially unless noted as parallel
Activity / Consent Type | Minimum Duration | Maximum Duration | Unit | AI Selection Logic & Programme Placement
PLANNING CONSENTS — Stage 3 (run in parallel with Developed Design where possible)
Full Planning Permission | 8 | 13 | wks | Statutory determination period. Submit at start of Stage 3. Does NOT add sequentially if run in parallel with Stage 3 design — flag as risk if Stage 3 duration is shorter than planning period.
Listed Building Consent (LBC) | 8 | 13 | wks | Run alongside full planning where possible. Dual-consent risk: if LBC determination is sequential to planning, add 8–13 weeks. Flag explicitly as HIGH risk in programme.
Prior Approval | 4 | 8 | wks | Apply when Q3.5 = Prior approval. Shorter period, typically residential/PD extensions. Place at start of Stage 3.
Change of Use Consent | 8 | 13 | wks | Apply when Q2.3 = Modification with change of use or when Q3.5 flags change of use. Same statutory period as full planning.
Permitted Development — No Consent | 0 | 0 | wks | No programme allowance needed. Confirm PD applies via pre-application check if unsure.
Pre-Application Advice (where required) | 4 | 6 | wks | Add when Q3.5 = Unsure or Q1.4 = Pre-1900. Pre-app advice before formal submission. Place at end of Stage 2.
BUILDING CONTROL — Stage 3/4 boundary (Full Plans route recommended for all commercial / estates projects)
Building Control — Local Authority (LABC) Full Plans Submission | 5 | 8 | wks | Statutory: 5 weeks or 2 months with consent. Allow 6–8 weeks in programme for commercial projects. Place at Stage 3/4 boundary. Inspections then continue throughout Stage 5 — no additional programme time.
Building Control — Private RBCA (Registered Building Control Approver) | 3 | 5 | wks | Faster and more flexible. Recommended for programme-critical projects. Allow 3–5 weeks. Same Full Plans route — Initial Notice submitted to LA. Lower end if early engagement with RBCA during Stage 3.
Higher Risk Buildings (HRB) — BSR Route (7+ storeys or complex mixed use) | 26 | 36 | wks | Building Safety Regulator (BSR) route for HRBs only. 2025 average: 36 weeks. Flag as CRITICAL PROGRAMME RISK if project is HRB. Must be identified at Stage 1.
PROCUREMENT & TENDER PERIODS — Threshold Rule: Over £100k = Formal Competitive Tender ¦ Under £100k = 3 Quotations
Formal Competitive Tender (Construction budget OVER £100,000) | 10 | 12 | wks | Apply when cost estimate mid-point exceeds £100k. Full ITT/ITP process required. Placed at Stage 4/5 boundary. Includes tender period + evaluation + contract award.
3 Quotations — Direct Approach (Construction budget UNDER £100,000) | 4 | 6 | wks | Apply when cost estimate mid-point is under £100k. Shorter quotation period acceptable. Allow 4–6 weeks including evaluation and award.
Design & Build — Employer's Requirements Tender (D&B procurement route) | 10 | 12 | wks | Apply when D&B route selected (Q5.2). Same 10–12 / 4–6 week threshold rule applies. Contractor appointed at end of Stage 2 or 3.
PCSA Period (Pre-Construction Services Agreement) | 8 | 16 | wks | Apply when PCSA route selected. Runs alongside Stage 2–3 design. Show as parallel bar in programme. Main contract awarded at end of PCSA following open-book pricing agreement.
Two-Stage Tender — Stage 1 (Prelims / OH&P selection) | 6 | 8 | wks | First stage: select contractor on overhead and profit. Place at end of Stage 2.
Two-Stage Tender — Stage 2 (Full pricing at Stage 4) | 6 | 8 | wks | Second stage: full price agreed at Stage 4 completion. Both stages shown explicitly in programme.

## Construction Duration
ESTATES AI TOOL ¦ Programme Duration Reference — Construction Duration Benchmarks
Version 2.0 ¦ May 2026 ¦ Durations in weeks ¦ Based on RIBA Stage 5 only (excludes handover)
Project Type | Up to 250 m² | 250 – 500 m² | 500 – 1,500 m² | 1,500 – 3,000 m² | Unit | Complexity Uplifts & AI Selection Logic
PROJECT TYPE — CONSTRUCTION DURATIONS (RIBA Stage 5)
Internal Fit-Out — Basic / Cat A (offices, general academic space) | 4 – 6 | 6 – 10 | 10 – 16 | 16 – 26 | wks | Cat A: partitions, ceiling, floor, M&E first fix and second fix. Occupied uplift: add 20–30%. Basic = lower end.
Internal Fit-Out — Cat B / High Spec (bespoke finishes, joinery, AV) | 5 – 8 | 8 – 12 | 12 – 20 | 20 – 32 | wks | Bespoke joinery, feature ceilings, specialist finishes extend programme. Cat B always at upper end of range.
Specialist Fit-Out — Labs / Healthcare (M&E-heavy, containment, cleanroom) | 8 – 12 | 12 – 18 | 18 – 28 | 28 – 44 | wks | High M&E content — commissioning and validation extend construction period significantly. Always use upper end.
Refurbishment — Fabric / Envelope (roof, facade, windows, waterproofing) | 4 – 6 | 6 – 10 | 10 – 18 | 18 – 28 | wks | Weather dependency adds risk. Listed buildings at upper end. Winter works may extend further.
Refurbishment — M&E Replacement (full or partial services replacement) | 5 – 8 | 8 – 14 | 14 – 22 | 22 – 36 | wks | Phased shutdowns for live buildings add duration. Fully vacant = lower end. Occupied = upper end + 20–30%.
Extension — Single Storey (structural frame + fit-out) | 8 – 12 | 12 – 18 | 18 – 26 | — | wks | Groundworks + frame + envelope + fit-out in sequence. Brownfield or contaminated ground = add 4–6 weeks.
Extension — Multi-Storey (2+ floors, structural frame) | 12 – 18 | 18 – 26 | 26 – 40 | 36 – 52 | wks | Steel or RC frame + multiple floor fits. Procurement of structural steelwork: allow 8–12 weeks lead time.
New Build — Standard Commercial (office, education, general purpose) | 16 – 22 | 22 – 34 | 30 – 48 | 44 – 64 | wks | Full new build: groundworks, frame, envelope, M&E, fit-out. Larger = always upper end. Seasonal risk applies.
External Works Only (landscaping, car park, drainage, paths) | 2 – 4 | 4 – 6 | 6 – 10 | 10 – 16 | wks | Weather and ground conditions drive duration. Winter start = add 2–4 weeks. Utility diversions = add 4–8 weeks.
Enabling Works / Demolition Only | 2 – 3 | 3 – 5 | 4 – 8 | 6 – 12 | wks | Asbestos removal adds 1–4 weeks depending on volume. Structural demolition requires propping — allow extra.
MANDATORY UPLIFTS — Apply on top of base construction duration above
Occupied During Works — Full occupation throughout | + 25% – 35% | — | — | — | % | Phasing, out-of-hours working, noise & dust management, increased supervision. Use 30% as default mid-point.
Occupied During Works — Partial / phased | + 15% – 25% | — | — | — | % | Section-by-section handover. Use 20% as default. Programme shows phased completion sequence.
Access Restrictions — Term-time only working | + 15% – 20% | — | — | — | % | Works only permitted outside academic term. Effective working weeks reduced significantly. Flag as risk.
Access Restrictions — Restricted hours (e.g. 8am–4pm only, no nights) | + 10% – 15% | — | — | — | % | Lost productivity on multi-trade activities. Plant movements limited. Add 10% minimum.
Handover (RIBA Stage 6) (Commissioning, snagging, PC) | 2 – 4 | 2 – 4 | 3 – 6 | 4 – 8 | wks | Always shown separately after construction. Includes commissioning, snagging, and Practical Completion sign-off.

## AI Selection Logic
ESTATES AI TOOL ¦ Programme Module — AI Selection Logic Reference
This tab summarises how the AI should select durations from the reference tables above. For Claude Code prompt construction.
Decision Point | Questionnaire Input(s) | Programme Action
Which size band to use for design stage and construction durations | Q1.5 — Approximate project size (m²) | < 500 m² = Small. 500–2,000 m² = Medium. > 2,000 m² = Large. Use size band columns from Design Stage Durations and Construction Duration tabs.
When to include Asbestos Survey in programme | Q1.4 (building age), Q3.4 (known building issues), Q2.2 (demolition or structural works ticked) | Pre-1980 building → management survey. Demolition or structural alterations → refurb/demolition survey. Both triggers → use refurb/demolition survey duration (longer). Place at start of Stage 2.
When to include Structural Survey | Q3.4 (structural concerns ticked), Q2.2 (structural alterations ticked) | Either trigger = include structural survey, 2–3 weeks at start of Stage 2.
When to include Ground Investigation | Q1.2 (new build or extension), Q1.3 (brownfield), Q3.4 (contaminated land) | New build or brownfield or contaminated = include ground investigation, 3–6 weeks. Place at Stage 2 start alongside other surveys.
Design stage duration — which end of range | Q2.2 (scope complexity), Q1.4 (building age), Q2.5 (standards), Q3.2 (occupation) | Lower end: simple scope, no structural alterations, vacant building. Upper end: structural alterations, M&E-heavy, listed building, BREEAM/specialist standards, occupied.
Planning consent — which type and duration | Q3.5 (planning consents required), Q1.4 (listed building probability) | Full planning = 8–13 weeks at Stage 3. LBC alongside = dual-consent risk, flag explicitly. Pre-app if unsure = add 4–6 weeks. Permitted development = no allowance.
Building control route — LABC vs private RBCA | Q3.1 (target completion date — programme-critical?), Q1.4 (conservation area risk) | Programme-critical project → recommend private RBCA (3–5 weeks). Standard project → LABC (6–8 weeks). HRB (7+ storeys) → BSR route, flag 26–36 weeks as critical risk.
Procurement — formal tender vs 3 quotations | Cost estimate mid-point (generated by cost module) | Mid-point > £100k → formal competitive tender, 10–12 weeks. Mid-point < £100k → 3 quotations, 4–6 weeks. Place at Stage 4/5 boundary.
Construction duration — which type and size band | Q1.2 (project type), Q1.3 (building use), Q2.2 (scope), Q1.5 (m²) | Match project type to Construction Duration tab row. Apply size band column. Add occupancy uplift from Q3.2. Add access uplift from Q3.3.
Occupancy uplift on construction duration | Q3.2 (occupation during construction) | Fully occupied = +25–35%. Partially occupied = +15–25%. Full decant or vacant = no uplift. Apply to base construction duration.
Target completion date feasibility check | Q3.1 (target completion date) | Sum all stage durations, surveys, regulatory periods, procurement, construction, and handover. Compare total to target. If unreachable → flag as HIGH risk. State minimum realistic end date.
Overall programme summary — one-line output | All questionnaire inputs, all duration selections above | AI outputs: total weeks from project start, broken into: [Pre-Design] + [Stage 2] + [Stage 3 / Planning] + [Stage 4 / BC] + [Tender] + [Construction] + [Handover]. Show as a single bar chart / Gantt with key milestone markers and target end date.

## Programme Assumptions
ESTATES AI TOOL ¦ Standard Programme Assumptions — Include in every report
These assumptions must be included verbatim (or adapted to project) in every programme section of a generated report.
STANDARD ASSUMPTIONS — Populate in every programme section
A1 | Programme durations are indicative only and based on information provided at RIBA Stage 0–1. Actual durations to be confirmed at Stage 2 once surveys, design scope, and procurement strategy are finalised.
A2 | Durations assume client decision-making within 2 weeks of each gateway submission. Delays beyond this will extend the programme accordingly.
A3 | Planning determination periods are based on statutory LPA timescales. No allowance has been made for delays due to information requests, committee referral, objections, or appeals.
A4 | Building control approval durations are indicative and based on [LABC / private RBCA route]. Inspections during construction are not shown as separate programme items — they are assumed to be concurrent with construction activities.
A5 | Construction duration is benchmarked against [X m² of [project type]] at standard productivity rates. Actual duration to be confirmed at Stage 2 by the appointed contractor or QS.
A6 | If the building is occupied during works, a programme uplift of [X%] has been applied for access management, phasing, noise and dust control, and increased supervision requirements.
A7 | Surveys identified as required but not yet commissioned are shown at the start of Stage 2. Commissioning and completing surveys before Stage 2 design commences will be a gateway condition.
A8 | The programme does not show calendar dates as the project start date is not confirmed at Stage 1. Durations are shown as weeks from a notional project start (Week 0 = Gateway 1 approval).
A9 | Procurement threshold rule applied: construction estimate mid-point [above / below] £100,000. [Formal competitive tender 10–12 weeks / 3 quotations 4–6 weeks] applied accordingly.
A10 | Handover (RIBA Stage 6) includes commissioning, snagging, and Practical Completion sign-off. The defects liability period is not shown in the programme — it begins at Practical Completion and is typically 12 months.