## 0. Read Me
Projento — Procurement Reference v2
Version | 2.3 · 11 October 2026 · Nabil Kayali · replaces v2.2 (routes renamed to the RIBA Plan of Work 2020: Design & Build 1 Stage, Design & Build 2 Stage, Management Contract / Construction Management; tab 5 gains the ▶ contract_rules table the app reads — Minor Works (MW / MWD / NEC4 ECS) under £1m and up to 500 m², and the CDP option under Traditional). Scores and tab 3 unchanged.
Purpose | Gives each feasibility report a preferred and an alternative option for four procurement decisions, driven by four project drivers.
DRIVERS (inputs)
Value | Construction cost excl. VAT — from the NRM1 workbook (mid-point).
Duration | Construction duration in weeks — from the Programme workbook.
Risk | Number of risks rated High in the report's risk register.
Client top priority | Q4.4 — the one thing that matters most.
OUTPUTS
Procurement route | Traditional · Design and build · Two-stage (PCSA) · Construction management
Commercial model | Lump sum · GMP · Target cost · Remeasurement · Cost reimbursable
Route to market | Quotations · Open tender · Selective tender · Framework mini-competition · Framework direct award · Negotiated
Contract type | JCT form and the NEC4 equivalent
HOW THE APP DECIDES
1. Set levels | For each driver, take the highest level in tab 1 whose 'From' the project meets.
2. Score | For each option in tab 2, read the four scores for those levels: 2 = good fit, 1 = possible, 0 = poor fit, X = not suitable (drop the option). Score = value + duration + risk + (2 × priority). Weights are in tab 1; maximum score is 10.
3. Client filter | Drop 'Public only' options for private clients and 'Private only' options for public clients.
4. Procurement route | Highest score = Preferred; second = Alternative. A tie goes to the option listed first.
5. Commercial model | Score only the models whose 'Works with routes' includes the route. Pick the best for the preferred route and the best for the alternative route.
6. Contract type | Look up route + model in tab 3. Use the JCT column for the value band and show the NEC4 option alongside.
7. Route to market | Highest score = Preferred; second = Alternative.
8. Report text | Build the section from the 'What it is', 'Best when' and 'Watch-outs' cells. The AI must not name any option or contract that is not in this workbook.
CHECK TAB | Tab 4 runs the same rules with formulas. Change the yellow cells to test any project. The app does not read tab 4.
APP CHANGES NEEDED
Top priority | Q4.4 is multi-select. Add a follow-up: 'Which ONE matters most?' using the same seven options.
Client type | Add 'Is the client a public-sector body?' (Yes / No). Framework options are shown only when Yes.
Wiring | Add env var PROCUREMENT_FILE_URL and include this file in /api/rates-check.
Editing | Level names in tab 1 column C must match the score column headings in tab 2 exactly.
BASIS
Works threshold | £5,193,000 incl. VAT — Procurement Act 2023 (Threshold Amounts) (Amendment) Regulations 2025, for procurements started from 1 January 2026.
Scores and contract mapping | Standard UK practice (JCT and NEC4 guidance, RICS and RIBA procurement guidance) applied by Claude. Review with a QS or procurement lead before relying on them.
Contract editions | Use the current edition of each form (JCT 2024 editions where published).
Disclaimer | Guidance for RIBA Stage 0–1 feasibility only. Not legal or procurement advice.

## 1. Drivers
Driver | Code | Level (column name in tab 2) | From (project value is at least) | Questionnaire answer / meaning | Source in the app
Value | V0 | V0 Under £100k | 0 | Construction cost excl. VAT (£) | NRM1 workbook — construction cost mid-point, excl. VAT
Value | V1 | V1 Under £1m | 100000 | Construction cost excl. VAT (£) | NRM1 workbook — construction cost mid-point, excl. VAT
Value | V2 | V2 £1m to threshold | 1000000 | Construction cost excl. VAT (£) | NRM1 workbook — construction cost mid-point, excl. VAT
Value | V3 | V3 Threshold to £20m | 4327500 | Construction cost excl. VAT (£) | NRM1 workbook — construction cost mid-point, excl. VAT
Value | V4 | V4 Over £20m | 20000000 | Construction cost excl. VAT (£) | NRM1 workbook — construction cost mid-point, excl. VAT
Duration | D1 | D1 Up to 26 wks | 0 | Construction duration (weeks) | Programme workbook — construction duration
Duration | D2 | D2 27–52 wks | 27 | Construction duration (weeks) | Programme workbook — construction duration
Duration | D3 | D3 Over 52 wks | 53 | Construction duration (weeks) | Programme workbook — construction duration
Risk | R1 | R1 Low | 0 | 0–1 risks rated High | Report risk register — count of risks rated High
Risk | R2 | R2 Medium | 2 | 2–3 risks rated High | Report risk register — count of risks rated High
Risk | R3 | R3 High | 4 | 4 or more risks rated High | Report risk register — count of risks rated High
Client top priority | P1 | P1 Lowest cost |  | Lowest cost | Q4.4 — the one that matters most
Client top priority | P2 | P2 Fixed/certain final cost |  | Fixed/certain final cost | Q4.4 — the one that matters most
Client top priority | P3 | P3 Speed |  | Speed | Q4.4 — the one that matters most
Client top priority | P4 | P4 Design quality |  | Design quality | Q4.4 — the one that matters most
Client top priority | P5 | P5 Flexibility |  | Flexibility | Q4.4 — the one that matters most
Client top priority | P6 | P6 Minimise disruption |  | Minimise disruption | Q4.4 — the one that matters most
Client top priority | P7 | P7 Funder/compliance requirement |  | Funder/compliance requirement | Q4.4 — the one that matters most
WEIGHTS
Weight — Value |  |  | 1
Weight — Duration |  |  | 1
Weight — Risk |  |  | 1
Weight — Client top priority |  |  | 2 | Priority counts double: it is the client's explicit steer.
KEY FIGURE
Works threshold incl. VAT (£) |  |  | 5193000 | Legal threshold for public works contracts. Review every two years.
Works threshold excl. VAT (£) |  |  | 4327500 | Used as the start of value level V3.
Note on D28: Procurement Act 2023 (Threshold Amounts) (Amendment) Regulations 2025, from 1 Jan 2026. Next review expected 1 Jan 2028.

## 2. Options
ID | Output | Option | What it is | Best when | Watch-outs | Works with routes | Client | V0 Under £100k | V1 Under £1m | V2 £1m to threshold | V3 Threshold to £20m | V4 Over £20m | D1 Up to 26 wks | D2 27–52 wks | D3 Over 52 wks | R1 Low | R2 Medium | R3 High | P1 Lowest cost | P2 Fixed/certain final cost | P3 Speed | P4 Design quality | P5 Flexibility | P6 Minimise disruption | P7 Funder/compliance requirement | Project types
PR1 | Procurement route | Traditional | The client's design team completes the design; contractors then price and build it. The client keeps design control. | Design can be completed before tender; cost certainty and design quality matter more than speed. | Slowest route to site. Gaps in the design become client variations. Little contractor input to buildability. |  | All | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 2
PR2 | Procurement route | Design & Build 1 Stage | The client sets its requirements; one contractor designs and builds for an agreed price. The client's designers may be novated to the contractor. | Requirements are clear and the client wants one point of responsibility and price certainty. | Quality depends on how well the requirements are written. Less control of detail. Changes after award are expensive. |  | All | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 1 | 1
PR3 | Procurement route | Design & Build 2 Stage | A contractor is appointed early under a pre-construction services agreement on fees and prelims, helps develop the design, then prices the works open-book for the second stage. | Complex, occupied or phased work, or poor existing information, where early contractor input to sequencing and buildability pays off. | Less price competition at the second stage. Needs a strong cost consultant to test the price. Scope creep if not controlled. |  | All | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 2 | 1 | 1 | 2 | 1
PR4 | Procurement route | Management Contract / Construction Management | The client contracts directly with each trade contractor; a construction manager is paid a fee to manage them. | Large, complex or fast-track projects where the client is experienced and wants direct control of quality and change. | The client carries most of the cost and interface risk. No overall price until the last package is let. Needs an experienced client team. |  | All | X | X | X | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 0
CM1 | Commercial model | Lump sum | One agreed price for a defined scope; the contractor carries the risk of its own pricing. | Scope and design are well defined and the client wants a firm price at award. | Unclear or changing scope leads to variations and claims. Contractors add risk allowances where information is poor. | PR1; PR2; PR3 | All | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 2
CM2 | Commercial model | Guaranteed maximum price (GMP) | The contractor guarantees a ceiling price; the client usually shares any saving below it. | Larger design and build work where the client needs a firm upper limit before the design is complete. | Contractors price the cap with a risk premium. No standard form — needs legal amendments. Define clearly what can move the cap. | PR2; PR3 | All | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 1
CM3 | Commercial model | Target cost | A target price is agreed; the contractor is paid actual cost plus fee, and overruns or savings are shared by an agreed formula. | Uncertain or evolving scope where client and contractor work together to control cost. | No firm final price. Needs open-book cost auditing and an experienced client team. | PR1; PR2; PR3 | All | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 1 | 2 | 2 | 0
CM4 | Commercial model | Remeasurement | Priced against approximate quantities or a schedule of rates; the work is measured as built and paid at the tendered rates. | The type of work is known but not its quantity — repairs, refurbishment with hidden conditions, or rolling programmes. | Final cost is only known at the end. Needs a reliable estimate of quantities and regular measurement. | PR1 | All | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 0 | 2 | 1 | 2 | 1 | 1 | External works only
CM5 | Commercial model | Cost reimbursable | The contractor is paid its actual costs plus an agreed fee. | Urgent work that cannot be defined in time to price, or management-led routes. | Lowest cost certainty and weakest incentive to save. Needs tight cost control and auditing. | PR1; PR4 | All | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 1 | 0
RM1 | Route to market | Quotations | Written quotations from at least three suitable contractors against a clear specification. | Low-value, simple, well-defined work within the client's standing-order limit. | Only within standing-order limits (often £50k–£250k). A weak specification leads to disputes. CDM duties still apply. |  | All | 2 | X | X | X | X | 2 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 0
RM2 | Route to market | Open tender | Advertised publicly; any contractor meeting the conditions may bid. | The client wants maximum competition and a transparent audit trail. | Slowest route. Many bids to evaluate. Public bodies above the threshold must follow the Procurement Act 2023. |  | All | 1 | 1 | 2 | 2 | 1 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2
RM3 | Route to market | Selective tender | A shortlist of 4–6 suitable contractors is invited to tender. | The client wants competition among contractors of proven capability. | Public bodies above the threshold need a compliant procedure (e.g. competitive flexible) to shortlist. Prequalification takes time. |  | All | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2
RM4 | Route to market | Framework — mini-competition | A competition among contractors already appointed to a public-sector framework. | Public clients who want competition with pre-vetted contractors and standard terms, faster than an open tender. | Public and eligible bodies only. Check the lot's scope, value band, region and expiry. Framework fees may apply. |  | Public only | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2
RM5 | Route to market | Framework — direct award | Direct appointment of one framework contractor, where the framework rules allow. | Speed is critical, or early engagement with a proven contractor is needed (often with two-stage). | Public and eligible bodies only. Less price competition — needs a strong cost consultant. Must follow the framework's award rules. |  | Public only | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 2 | 1 | 2 | 2 | 1
RM6 | Route to market | Negotiated | The client negotiates directly with one chosen contractor. | Private clients with a trusted contractor, urgent work, or a follow-on phase. | No competition, so value must be tested by a cost consultant. Not normally open to public bodies. |  | Private only | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 0 | 1 | 2 | 1 | 2 | 2 | 0
Scores: 2 = good fit · 1 = possible · 0 = poor fit · X = not suitable. Basis: standard UK practice applied by Claude — review before relying on it.

## 3. Contracts
Key (route¦model) | Route + commercial model | JCT — V0/V1 under £1m | JCT — V2 £1m to threshold | JCT — V3/V4 above threshold | NEC4 equivalent | Notes
PR1¦CM1 | Traditional + Lump sum | JCT Minor Works (MW) for simple work; JCT Intermediate (IC) if more complex | JCT Intermediate (IC); ICD where the contractor designs part (e.g. M&E) | JCT Standard Building Contract with Quantities (SBC/Q) or without Quantities (SBC/XQ) | ECC Option A (priced contract with activity schedule); ECSC for simple low-value work | Tender on a full specification or bills of quantities.
PR1¦CM3 | Traditional + Target cost | Not typical at this value | JCT Constructing Excellence (CE) with target cost | JCT Constructing Excellence (CE) with target cost | ECC Option C (target, activity schedule) or Option D (target, bill of quantities) | Open-book cost auditing needed.
PR1¦CM4 | Traditional + Remeasurement | JCT Measured Term Contract (MTC) for a programme of small works; otherwise SBC with Approximate Quantities (SBC/AQ) | JCT SBC with Approximate Quantities (SBC/AQ) | JCT SBC with Approximate Quantities (SBC/AQ) | ECC Option B (priced contract with bill of quantities); Term Service Contract (TSC) for a programme | Regular measurement needed through the works.
PR1¦CM5 | Traditional + Cost reimbursable | JCT Prime Cost Building Contract (PCC) | JCT Prime Cost Building Contract (PCC) | JCT Prime Cost Building Contract (PCC) | ECC Option E (cost reimbursable) | Use only for urgent or undefinable work; needs tight cost control.
PR2¦CM1 | Design and build + Lump sum | JCT Minor Works with Contractor's Design (MWD) | JCT Design and Build (DB); ICD where the contractor designs only part | JCT Design and Build (DB) | ECC Option A with contractor's design | Quality depends on the Employer's Requirements.
PR2¦CM2 | Design and build + GMP | Not typical at this value | JCT Design and Build (DB) with GMP amendments | JCT Design and Build (DB) with GMP amendments | ECC Option C with a price cap (bespoke Z clause) | No standard GMP form — amendments need legal input.
PR2¦CM3 | Design and build + Target cost | Not typical at this value | JCT Constructing Excellence (CE) with contractor's design and target cost | JCT Constructing Excellence (CE) with contractor's design and target cost | ECC Option C with contractor's design | Open-book cost auditing needed.
PR3¦CM1 | Two-stage + Lump sum | Not typical at this value | JCT Pre-Construction Services Agreement (PCSA), then JCT DB (or SBC) | JCT Pre-Construction Services Agreement (PCSA), then JCT DB (or SBC) | First stage under NEC4 Professional Service Contract (PSC); construction under ECC Option A | Test the second-stage price against benchmarks before signing.
PR3¦CM2 | Two-stage + GMP | Not typical at this value | JCT PCSA, then JCT DB with GMP amendments | JCT PCSA, then JCT DB with GMP amendments | ECC Option C with Option X22 (early contractor involvement) and a price cap (Z clause) | No standard GMP form — amendments need legal input.
PR3¦CM3 | Two-stage + Target cost | Not typical at this value | JCT PCSA, then JCT Constructing Excellence (CE) with target cost | JCT PCSA, then JCT Constructing Excellence (CE) with target cost | ECC Option C with Option X22 (early contractor involvement) | Common NEC4 model for complex public work.
PR4¦CM5 | Construction management + Cost reimbursable | Not typical at this value | Not typical at this value | JCT Construction Management Appointment (CM/A) and Trade Contracts (CM/TC); or JCT Management Building Contract (MC) | PSC for the construction manager and ECC for each trade package; or ECC Option F (management contract) | Trade packages are usually lump sum; the overall cost is not fixed until the last package is let.

## 4. Check
Check — test any project
Change the yellow cells. Same rules as the app; the app does not read this tab.
Input | Value | Level
Construction cost (£, excl. VAT) | 10000000 | V3 Threshold to £20m
Construction duration (weeks) | 40 | D2 27–52 wks
Number of risks rated High in the risk register | 5 | R3 High
Client top priority (Q4.4) | Fixed/certain final cost | P2 Fixed/certain final cost
Public-sector client? | No
Output | Preferred | Score | Alternative | Score | Pref. ID | Alt. ID
Procurement route | Design & Build 1 Stage | 9 | Traditional | 7 | PR2 | PR1
Commercial model | Lump sum | 8 | Lump sum | 8 | CM1 | CM1
Contract — JCT | JCT Design and Build (DB) |  | JCT Standard Building Contract with Quantities (SBC/Q) or without Quantities (SBC/XQ)
Contract — NEC4 | ECC Option A with contractor's design |  | ECC Option A (priced contract with activity schedule); ECSC for simple low-value work
Route to market | Selective tender | 8 | Open tender | 7 | RM3 | RM2
Maximum score: 10. Commercial model and contract in the Alternative column go with the alternative route.
WORKINGS
ID | Output | Option | Value | Duration | Risk | Priority | Excluded | Score | Rank score (pref.) | Rank score (alt.) | Rank (pref.) | Rank (alt.)
PR1 | Procurement route | Traditional | 1 | 2 | 0 | 2 | No | 7 | 6.98 | 6.98 | 2 | 2
PR2 | Procurement route | Design & Build 1 Stage | 2 | 2 | 1 | 2 | No | 9 | 8.979 | 8.979 | 1 | 1
PR3 | Procurement route | Design & Build 2 Stage | 2 | 1 | 2 | 1 | No | 7 | 6.978 | 6.978 | 3 | 3
PR4 | Procurement route | Management Contract / Construction Management | 0 | 1 | 2 | 0 | No | 3 | 2.977 | 2.977 | 4 | 4
CM1 | Commercial model | Lump sum | 2 | 2 | 0 | 2 | No | 8 | 7.976 | 7.976 | 1 | 1
CM2 | Commercial model | Guaranteed maximum price (GMP) | 2 | 1 | 1 | 2 | No | 8 | 7.975 | -100.025 | 2 | 5
CM3 | Commercial model | Target cost | 2 | 1 | 2 | 0 | No | 5 | 4.974 | 4.974 | 3 | 2
CM4 | Commercial model | Remeasurement | 1 | 2 | 2 | 0 | No | 5 | -100.027 | 4.973 | 4 | 3
CM5 | Commercial model | Cost reimbursable | 0 | 1 | 2 | 0 | No | 3 | -100.028 | 2.972 | 5 | 4
RM1 | Route to market | Quotations | X | 1 | 0 | 1 | Yes |  | -100.029 | -100.029 | 4 | 4
RM2 | Route to market | Open tender | 2 | 1 | 0 | 2 | No | 7 | 6.97 | 6.97 | 2 | 2
RM3 | Route to market | Selective tender | 1 | 2 | 1 | 2 | No | 8 | 7.969 | 7.969 | 1 | 1
RM4 | Route to market | Framework — mini-competition | 2 | 2 | 2 | 2 | Yes |  | -100.032 | -100.032 | 5 | 5
RM5 | Route to market | Framework — direct award | 2 | 2 | 2 | 1 | Yes |  | -100.033 | -100.033 | 6 | 6
RM6 | Route to market | Negotiated | 1 | 1 | 2 | 1 | No | 6 | 5.966 | 5.966 | 3 | 3

## 5. Routes and contracts
PROCUREMENT ROUTES AND THEIR CONTRACTS — RIBA Plan of Work 2020
The route decides WHEN the contractor is brought in and who designs; the contract is chosen WITHIN the route; the route to market (tab 2) decides how long the tender takes. The table above is reference; the app reads the ▶ contract_rules table below. The programme timing for each route is on the Programme workbook's 'Procurement' sheet.
Route (RIBA) | Contractor brought in | Contract | Form | Use it when | Value | Programme effect
Traditional | Tender at the end of Stage 4 | Minor Works Building Contract (MW) | JCT | Simple work fully designed by the client's team; refurbishment, fit-out or external works; no specialist design | Up to £1m | Stage 3 and Stage 4 combined into one short design-and-specification stage
Traditional | Tender at the end of Stage 4 | Minor Works with Contractor's Design (MWD) | JCT | As MW, where the contractor designs one named part (e.g. ventilation) | Up to £1m | As MW
Traditional | Tender at the end of Stage 4 | Engineering and Construction Short Contract (ECS) | NEC4 | Simple, low-risk work (NEC4 equivalent of MW) | Up to £1m | As MW
Traditional | Tender at the end of Stage 4 | Intermediate Building Contract (IC) | JCT | Medium-sized work fully designed by the client's team | £1m to threshold | None
Traditional | Tender at the end of Stage 4 | Intermediate with Contractor's Design (ICD) — CDP option | JCT | As IC, where the contractor designs named parts (services, cladding, roofing systems) | £1m to threshold | Client's Stage 4 shorter (named parts by performance specification)
Traditional | Tender at the end of Stage 4 | Standard Building Contract with / without Quantities (SBC) | JCT | Large or complex work fully designed by the client | Above threshold | None
Traditional | Tender at the end of Stage 4 | Standard Building Contract with Contractor's Designed Portion (SBC + CDP) — CDP option | JCT | As SBC, where the contractor designs named parts | Above threshold | Client's Stage 4 shorter
Traditional | Tender at the end of Stage 4 | Engineering and Construction Contract (ECC) Option A or B | NEC4 | Priced contract with activity schedule (A) or bill of quantities (B) | Any | None
Traditional | Tender at the end of Stage 4 | Measured Term Contract (MTC) / Prime Cost (PCC) | JCT | Repeat or term works (MTC); urgent or undefined work (PCC) | Any | None
Design & Build 1 Stage | Employer's Requirements at the end of Stage 3; contractor appointed at the start of Stage 4 | Design and Build Contract (DB) | JCT | Client can state clear requirements; one point of responsibility | £1m and above | Tender after Stage 3; the contractor does Stage 4 after award, then builds
Design & Build 1 Stage | Employer's Requirements at the end of Stage 3 | Minor Works with Contractor's Design (MWD) | JCT | Small design and build work | Up to £1m | As DB
Design & Build 1 Stage | Employer's Requirements at the end of Stage 3 | ECC Option A with contractor's design | NEC4 | NEC4 equivalent of DB | Any | As DB
Design & Build 2 Stage | Employer's Requirements at the end of Stage 2; contractor under a PCSA through Stage 3; price agreed and appointed at the start of Stage 4 | Pre-Construction Services Agreement (PCSA), then DB or Constructing Excellence (CE) | JCT | Complex or time-critical projects needing early contractor input | £1m and above | First-stage tender after Stage 2 alongside Stage 3; second-stage price at the end of Stage 3; contractor does Stage 4, then builds
Design & Build 2 Stage | As above | ECC Option C with Option X22 (early contractor involvement) | NEC4 | NEC4 equivalent, target cost | £1m and above | As above
Management Contract / Construction Management | Contractor appointed at the end of Stage 2 | Management Building Contract (MC) / Construction Management Appointment + trade contracts | JCT | Large, complex projects designed and let package by package | Above threshold | Appointment after Stage 2 alongside Stage 3; packages tendered during Stage 4; site work after Stage 4
Management Contract / Construction Management | As above | ECC Option F (management contract) | NEC4 | NEC4 equivalent | Above threshold | As above
▶ contract_rules | Read by the app. Within the Traditional route: Minor Works (MW, or MWD with one specialist item) when every MW rule holds; otherwise the CDP option when the scope has at least CDP-SERVICES-MIN services items. Lists are separated by ";".
Rule | Value | Meaning
MW-VALUE-MAX | 1000000 | Construction cost below this (£, excl. VAT) — owner, 11 Oct 2026
MW-SIZE-MAX | 500 | Floor area (Q1.5, m²) at or below this — owner, 11 Oct 2026
MW-PROJECT-TYPES | Refurbishment; Fit-out; External works only | Project types (Q1.2) that can use Minor Works
MW-EXCLUDE-LEVELS | Reconfiguration or full redesign | Levels of intervention (Q2.2) that rule Minor Works out
MW-SPECIALIST | Laboratory; Clinical; Cleanroom; Medical gases; Fume extraction; Lifts; Sprinklers; Smoke ventilation | Scope items needing specialist design: none = MW, exactly one = MWD, more = not Minor Works
MW-JCT | JCT Minor Works Building Contract (MW) | Contract shown for Minor Works
MWD-JCT | JCT Minor Works Building Contract with Contractor's Design (MWD) | Contract shown when one specialist item is contractor-designed
MW-NEC4 | NEC4 Engineering and Construction Short Contract (ECS) | NEC4 equivalent for Minor Works
CDP-SERVICES-MIN | 4 | Services (Group 5) items in the scope at or above which the CDP option is used
CDP-JCT-BELOW | JCT Intermediate Building Contract with Contractor's Design (ICD) | CDP contract below the works threshold
CDP-JCT-ABOVE | JCT Standard Building Contract with Contractor's Designed Portion (SBC + CDP) | CDP contract at or above the works threshold
CDP-NEC4 | NEC4 ECC Option A with contractor's design of named parts | NEC4 equivalent for the CDP option
No overlap | Owner (11 Oct 2026): work on site starts only when Stage 4 is complete, on every route. Contractor-led is not offered.