## README
ESTATES AI TOOL — PROGRAMME DURATION REFERENCE
Version | v4.6 · October 2026 · Nabil Kayali
Purpose | Single source of truth for all RIBA Stage 0-1 programme durations (weeks). Read by programmeCalculator.js at runtime. The AI never calculates time — it reads finished numbers from this workbook.
UNIFIED SIZE BANDS (one band scheme for design AND construction — replaces the old 4-band / 5-band split)
Code | GIFA range
S1 | < 150 m² (Very Small)
S2 | 150 – 250 m²
S3 | 250 – 500 m²
S4 | 500 – 1,500 m²
S5 | 1,500 – 3,000 m²
S6 | 3,000 – 10,000 m²
S7 | > 10,000 m² (Construction sheet only — a blank S7 cell, and every Durations row, falls back to S6)
The 250 m² boundary now falls cleanly on the S2/S3 line, so the Stage 3 gateway split works without a special case.
HOW THE CALCULATOR SHOULD ASSEMBLE A PROGRAMME
1 | Pick the size band (S1-S7) from Q1.5 GIFA.
2 | CRITICAL rows are summed in sequence: Stage 2 → Stage 3 → Stage 4 → Procurement → Construction → Handover.
3 | Apply the Q2.3 design multiplier (Modifiers tab) to Stage 2/3/4 ONLY. Do not scale UPLIFT or GATEWAY rows.
4 | Add UPLIFT rows (+weeks) where their Trigger is met. Add GATEWAY rows on the critical path.
5 | PARALLEL rows (surveys, building control) run alongside design and do NOT add to the total — UNLESS flagged critical (see Asbestos R&D note).
6 | PLANNING is parallel with Stage 3 but GATES Stage 4/Procurement: carry max(Stage 3, Planning). Stage 4/tender start only after consent unless the 'at-risk overlap' lever (FastTrack) is on.
7 | Apply construction uplifts from Modifiers to the Construction duration only: access (ACC, highest tier) × the HIGHER of occupation (OCC) and phasing (PH-1) — occupation and phasing are not stacked.
8 | Apply FastTrack levers where their Trigger is met — these remove/replace/compress rows and are how a user facilitates or skips pre-construction work.
9 | Add programme float (Modifiers PROG-FLOAT) to give a realistic date alongside the best-case date.
ILLUSTRATIVE ASSEMBLED PROGRAMMES (sense-check only — not read by the app)
400 m² occupied refurb, full systems (S3) | Stage2 3-4 + GW 2 + Stage3 4-6 (∥ planning 8-13 → carry 8-13) + GW 2 + Stage4 4-7 + Tender 10-14 + Constr 8-14 (+30% occ ≈ 10-18) + Handover 2-4 ≈ 39-57 wks
1,200 m² Cat B fit-out, vacant (S4) | Stage2 6-8 + GW 2 + Stage3 6-8 + GW 2 + Stage4 6-8 + Tender 10-14 + Constr 12-20 + Handover 3-6 ≈ 47-68 wks (no planning if internal fit-out)
1,500 m² new build standard (S5) | Stage2 8-10 + GW 2 + Stage3 8-12 (∥ planning 8-13) + GW 2 + Stage4 8-12 + Tender 10-14 + Constr 44-64 + Handover 4-8 ≈ 92-124 wks
CHANGELOG v4.2 → v4.3 · Added ACC-1 / ACC-2 access-constraint construction uplifts (Q3.5), low ×1.10 / high ×1.175, highest tier only. Replaces the hard-coded term-time/restricted multipliers — now editable here. · Q3.5 now drives BOTH a programme uplift AND risk-register seed entries (see coordination map / brief). CHANGELOG v4.1 → v4.2
· | Unified to 6 size bands (was design=4 / construction=5). One sizeBand() function now serves both.
· | Fixed Stage 3 gateway: 250 m² split now lands on S2/S3 boundary (S1-S2=0, S3+=2). Removes the 250-500 m² bug.
· | All ranges split into numeric Low/High columns. No more en-dash text strings or '—' N/A markers for the parser.
· | Added Sequence / ParallelWith / Trigger / ScaledByQ2.3 columns so critical-path logic is data-driven, not hard-coded.
· | Q2.3 design multiplier now OWNED here (Modifiers tab), not borrowed from the NRM1 workbook.
· | Added >3,000 m² (S6) construction band. Extension single-storey left blank above 1,500 m² (rare).
· | New FastTrack tab: skip/compress levers driven by questionnaire answers (at-risk overlap, framework procurement, enabling-works package, RBCA, survey reuse, PD route).
· | Ground Investigation raised to 4-10 wks (was 3-6) — realistic with procurement + lab + reporting.
· | Formal tender raised to 10-14 wks to reflect Procurement Act 2023 standstill.
· | Added programme float rule and updated assumptions A11-A12.
v4.4 | Added Durations rows SV7 (ecology / bat survey, parallel, 2–4 wks) and BS1 (Building Safety Regulator Gateway 2, critical, 12–24 wks), from docs/workbook-changes-sept-2026.md. Weeks illustrative. Found by the 21-report test run: the Gateway 2 and ecology stages the code supports never appeared because these rows were missing.
v4.5 | Durations checked against eight University of Warwick projects (Oct 2026: Riley Court, Lakeside, Claycroft, Whitefields, Co-op, Scarman, IBRB café, Computer Science). Handover CH1 cut to 0–3 wks (commissioning runs inside construction; 2 wks on Lakeside, Riley Court and Whitefields). Fit-out CF2 S1–S4 shortened (Co-op 885 m² 7 wks; IBRB café ≈ 3 wks). M&E refurb CR1 S1–S2 shortened (Scarman 5 wks). New size band S7 > 10,000 m² with CR1 S7 50–70 (Claycroft 17,172 m²: 74 wks planned, forecast ≈ 95). Occupation and phasing uplifts no longer multiply — the higher applies (Lakeside: occupied, 6 sections, 45 wks). Confirmed unchanged: tender TN1 10–14 (Lakeside 13 wks to award), demolition CD1 (Whitefields ≈ 14 wks), CR1 S6 (Riley Court 36 + 6 wks strip-out), planning PL1 (Riley Court 7 wks).
v4.6 | Pre-launch fixes (10 Oct 2026, test batch 3): TN4 negotiated tender (2–5 wks); ACC-1 / ACC-2 triggers follow the new Q3.5 wording; works limited to certain periods no longer take ACC-2 — the construction is fitted into the Q3.5a window, with HOL-1…HOL-6 (typical school holidays) on Modifiers.

## Durations
ID | Phase | Activity | S1_Lo | S1_Hi | S2_Lo | S2_Hi | S3_Lo | S3_Hi | S4_Lo | S4_Hi | S5_Lo | S5_Hi | S6_Lo | S6_Hi | Unit | Type | ParallelWith | ScaledByQ2.3 | Trigger | Notes
PRE-DESIGN SURVEYS — run in parallel with design; do not extend the total unless flagged critical
SV1 | Survey | Asbestos — Management Survey | 0 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | wks | PARALLEL | Stage2-3 | N | q1_4_age=Pre-2000 AND no demolition/structural | Refurb/fit-out in pre-2000 building, no intrusive works.
SV2 | Survey | Asbestos — R&D Survey | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | wks | CRITICAL-IF | Stage2-3 | N | q1_4_age=Pre-1980 OR demolition/structural OR asbestos known | Becomes CRITICAL (must precede intrusive design) when Q2.3=Reconfiguration or strip-out, or demolition in Q2.2.
SV3 | Survey | Structural Survey | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | wks | PARALLEL | Stage2-3 | N | q3_1=Structural OR structural alterations in q2_2 | Parallel with other surveys.
SV4 | Survey | Condition Survey | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | wks | PARALLEL | Stage2-3 | N | q1_2=Refurbishment/Fit-Out | Refurb only. Parallel.
SV5 | Survey | Topographic Survey | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 2 | 3 | wks | PARALLEL | Stage2-3 | N | q1_2=New Build/Extension/External | Parallel.
SV6 | Survey | Ground Investigation | 4 | 6 | 4 | 6 | 4 | 8 | 5 | 8 | 6 | 10 | 6 | 10 | wks | PARALLEL | Stage2-3 | N | q1_2=New Build/Extension OR contaminated land | Procurement + fieldwork + lab + factual/interpretive report. Parallel but long-lead.
RIBA DESIGN STAGES — sequential on the critical path; Stage 2/3/4 scaled by Q2.3 design multiplier (Modifiers)
DS2 | Design | Stage 2 — Concept Design | 1 | 2 | 3 | 4 | 3 | 4 | 6 | 8 | 8 | 10 | 10 | 12 | wks | CRITICAL | - | Y | Always (start point set by Q4.5) | Multiply by Q2.3 design multiplier. Add uplifts below if triggered.
DS2a | Design | Stage 2 Uplift — Structural | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | wks | UPLIFT | - | N | structural alterations in q2_2 | Not scaled by Q2.3.
DS2b | Design | Stage 2 Uplift — Listed/Heritage | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | wks | UPLIFT | - | N | q1_4_age=Pre-1900 OR q3_4=Listed Building Consent | Heritage consultant required. Not scaled.
DS3 | Design | Stage 3 — Developed Design | 2 | 3 | 4 | 6 | 4 | 6 | 6 | 8 | 8 | 12 | 10 | 14 | wks | CRITICAL | - | Y | Always (unless Q4.5 past Stage 3) | Apply Q2.3 multiplier. Planning submitted at start of Stage 3.
DS3a | Design | Stage 3 Uplift — M&E Heavy | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | wks | UPLIFT | - | N | 4+ M&E systems in q2_2 | Not scaled.
DS3b | Design | Stage 3 Uplift — Specialist | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | wks | UPLIFT | - | N | labs/clinical/data centre in q1_3 or q2_2 | Not scaled.
DS4 | Design | Stage 4 — Technical Design | 2 | 3 | 4 | 7 | 4 | 7 | 6 | 8 | 8 | 12 | 10 | 14 | wks | CRITICAL | - | Y | Always (unless Q4.5 = Stage 4 complete) | Apply Q2.3 multiplier. Building Control Full Plans submitted here.
DS4a | Design | Stage 4 Uplift — M&E/Specialist | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 4 | wks | UPLIFT | - | N | M&E-heavy OR specialist project | Not scaled.
CLIENT GATEWAYS — decision/sign-off points on the critical path
GW | Gateway | Client Gateway (after Stage 2 & after Stage 4) | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | wks | GATEWAY | - | N | Always — applied twice | Reduce/merge via FastTrack FT8 (delegated authority).
GW3 | Gateway | Client Gateway — after Stage 3 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | wks | GATEWAY | - | N | GIFA > 250 m² (S3 and larger) | S1-S2 (≤250 m²) proceed straight to Stage 4 — no Stage 3 review.
PLANNING CONSENTS — parallel with Stage 3 but GATE Stage 4 / tender (carry the longer of the two)
PL1 | Planning | Full Planning Permission | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | wks | PARALLEL-GATING | Stage3 | N | q3_4=Full planning | Statutory determination (minor 8 / major 13 wks). No allowance for committee/appeal.
PL2 | Planning | Listed Building Consent | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | wks | PARALLEL-GATING | Stage3 | N | q3_4=Listed Building Consent | Flag HIGH risk if sequential to full planning (dual consent).
PL3 | Planning | Prior Approval | 4 | 8 | 4 | 8 | 4 | 8 | 4 | 8 | 4 | 8 | 4 | 8 | wks | PARALLEL-GATING | Stage3 | N | q3_4=Prior approval | Shorter statutory period. Place at start of Stage 3.
PL4 | Planning | Change of Use | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | 8 | 13 | wks | PARALLEL-GATING | Stage3 | N | q3_4=Change of use | Same statutory period as full planning.
PL5 | Planning | Pre-Application Advice | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | wks | CRITICAL | - | N | q3_4=Unsure | Place at end of Stage 2 before formal application.
PL0 | Planning | Permitted Development (no application) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | wks | NONE | - | N | q3_4=Permitted development | No statutory wait. Confirm with LPA; consider PD notification where required.
BUILDING CONTROL — parallel with Stage 4 / construction
BC1 | BuildingControl | Building Control — LABC Full Plans | 2 | 4 | 2 | 4 | 2 | 4 | 5 | 8 | 5 | 8 | 6 | 10 | wks | PARALLEL | Stage4 | N | Always (standard route) | Runs parallel with Stage 4. RBCA is faster if programme-critical.
BC2 | BuildingControl | Building Control — RBCA (private) | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | wks | PARALLEL | Stage4 | N | FastTrack FT5 selected | Programme-critical only. Not available for Higher-Risk Buildings (BSR Gateway 2 applies).
TENDER / PROCUREMENT — sequential, between design and construction start
TN1 | Procurement | Tender — Formal Competitive | 6 | 8 | 8 | 10 | 10 | 14 | 10 | 14 | 10 | 14 | 10 | 14 | wks | CRITICAL | - | N | works cost > £100,000 (internal threshold) | Full ITT, evaluation, standstill, award. Procurement Act 2023 standstill included.
TN2 | Procurement | Tender — Three Quotations | 3 | 4 | 3 | 4 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | wks | CRITICAL | - | N | works cost < £100,000 (internal threshold) | Lighter route below internal competitive-tender threshold.
TN3 | Procurement | Framework / Call-Off | 3 | 4 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 6 | 4 | 6 | wks | CRITICAL | - | N | FastTrack FT4 selected | Pre-procured framework (e.g. SCAPE, Pagabo). Fastest compliant route.
TN4 | Procurement | Tender — Negotiated (single contractor) | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 5 | 3 | 5 | wks | CRITICAL | - | N | Procurement Reference route to market = Negotiated | Negotiation with one contractor on an agreed basis: no competition period, only pricing, review and award. Added v4.6 (Oct 2026) — the negotiated route used to take the 10–14 week formal tender (TN1).
SV7 | Survey | Ecology / bat survey | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | wks | PARALLEL | Stage2-3 | N | Q3.8 = Ecological features OR roof scope on a pre-2000 building | Seasonal: emergence surveys May–September only. A miss can cost a full year. Weeks illustrative (v4.4) — set from experience.
BS1 | BuildingSafety | Building Safety Regulator — Gateway 2 approval | 12 | 24 | 12 | 24 | 12 | 24 | 12 | 24 | 12 | 24 | 12 | 24 | wks | CRITICAL | - | N | Higher-risk building (derived from Section 1: 18 m+ or 7+ storeys, residential-type use) | Statutory 12 weeks, sequential after Stage 4 and Building Control, before tender award. Real-world determinations frequently exceed 20 weeks. Weeks illustrative (v4.4).

## Construction
ID | Project Type | S1_Lo | S1_Hi | S2_Lo | S2_Hi | S3_Lo | S3_Hi | S4_Lo | S4_Hi | S5_Lo | S5_Hi | S6_Lo | S6_Hi | S7_Lo | S7_Hi | Unit | Trigger / AI Selection Logic
CN1 | New Build — Standard | 14 | 18 | 16 | 22 | 22 | 34 | 30 | 48 | 44 | 64 | 60 | 84 |  |  | wks | q1_2=New Build AND use not Healthcare/Industrial/Specialist. Offices, education, student accommodation, general commercial.
CN2 | New Build — Healthcare / Specialist | 18 | 24 | 22 | 32 | 32 | 48 | 44 | 64 | 60 | 84 | 80 | 110 |  |  | wks | q1_2=New Build AND q1_3=Healthcare. High M&E, commissioning + validation.
CN3 | New Build — Industrial / Warehouse | 6 | 10 | 8 | 14 | 14 | 22 | 22 | 36 | 32 | 52 | 48 | 72 |  |  | wks | q1_2=New Build AND q1_3=Industrial. Steel portal frame, minimal fit-out.
CX1 | Extension — Single Storey | 7 | 10 | 8 | 12 | 12 | 18 | 18 | 26 | [6 empty] | wks | q1_2=Extension, single storey. Rare above 1,500 m² (bands left blank).
CX2 | Extension — Multi-Storey | 10 | 14 | 12 | 18 | 18 | 26 | 26 | 40 | 36 | 52 | 50 | 72 |  |  | wks | q1_2=Extension, multi-storey. Steelwork lead time 8-12 wks (see FastTrack FT6).
CR1 | Refurb — M&E Replacement | 3 | 5 | 4 | 6 | 8 | 14 | 14 | 22 | 22 | 36 | 32 | 50 | 50 | 70 | wks | Full/partial services replacement. Longest refurb row — use when 3+ M&E systems in q2_2. v4.5 (Oct 2026): S1–S2 shortened (Scarman toilets 71 m², 5-wk window); S7 (>10,000 m²) added from Claycroft (17,172 m², Morgan Sindall: 74 wks works planned Jun 2025–Dec 2026, occupied, three blocks in turn). Riley Court 3,850 m² (S6): 36 wks + 6 wks strip-out = 42.
CR2 | Refurb — Fabric / Envelope | 3 | 5 | 4 | 6 | 6 | 10 | 10 | 18 | 18 | 28 | 26 | 42 |  |  | wks | Roof, facade, windows, waterproofing. Use when M&E is not primary scope. Weather risk.
CF1 | Fit-Out — Cat B / High Spec | 4 | 6 | 5 | 8 | 8 | 12 | 12 | 20 | 20 | 32 | 30 | 46 |  |  | wks | q2_4=High. Bespoke joinery, feature ceilings, specialist finishes.
CF2 | Fit-Out — Basic / Cat A | 2 | 4 | 3 | 5 | 4 | 7 | 6 | 9 | 16 | 26 | 24 | 38 |  |  | wks | Standard offices/academic/retail/café. Partitions, ceiling, floor, M&E 1st+2nd fix. v4.5 (Oct 2026): S1–S4 shortened — Co-op store 885 m² 7 wks (Kingfisher, 2 of them 7-day working), IBRB café 72 m² ≈ 3 wks (Senevo prelims).
CS1 | Specialist — Labs / Healthcare | 6 | 10 | 8 | 12 | 12 | 18 | 18 | 28 | 28 | 44 | 40 | 60 |  |  | wks | Specialist rooms in q1_3/q2_2 regardless of project type. Commissioning + validation.
CE1 | External Works | 2 | 3 | 2 | 4 | 4 | 6 | 6 | 10 | 10 | 16 | 14 | 22 |  |  | wks | q1_2=External Works or external scope. Winter start adds 2-4 wks.
CD1 | Demolition / Enabling | 1 | 2 | 2 | 3 | 3 | 5 | 4 | 8 | 6 | 12 | 10 | 18 |  |  | wks | Asbestos removal adds 1-4 wks. Can be split to an early package (FastTrack FT7).
CH1 | Handover | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 3 |  |  | wks | Always added to construction. Snagging, Practical Completion, O&M manuals and client move-in only — commissioning runs inside the last weeks of construction. v4.5 (Oct 2026): 2 wks on Lakeside (tender programme), Riley Court (Maris) and Whitefields (H&S file); was up to 6-10 wks.

## Modifiers
ID | Modifier | Applies To | Type | Value | Trigger (questionnaire) | Notes
Q23-1 | Q2.3 Design multiplier — Fabric & finishes only | Stage 2/3/4 | MULTIPLIER | 0.5 | q2_3_interventionLevel=Fabric and finishes only | Also cost band ×0.80 (NRM1). Shortest design.
Q23-2 | Q2.3 Design multiplier — Finishes with minor services | Stage 2/3/4 | MULTIPLIER | 0.7 | q2_3_interventionLevel=Finishes with minor services | Cost band ×0.90 (NRM1).
Q23-3 | Q2.3 Design multiplier — Full systems replacement | Stage 2/3/4 | MULTIPLIER | 1 | q2_3_interventionLevel=Full systems replacement | Baseline. Cost band ×1.00 (NRM1).
Q23-4 | Q2.3 Design multiplier — Reconfiguration / full redesign | Stage 2/3/4 | MULTIPLIER | 1.3 | q2_3_interventionLevel=Reconfiguration or full redesign | Cost band ×1.15 (NRM1). Triggers Group 0 + structural uplift.
Q23-NB | Design multiplier — New build / no Q2.3 | Stage 2/3/4 | MULTIPLIER | 1 | q1_2=New Build/External/Demolition | Q2.3 not asked; baseline applies.
OCC-1 | Occupation uplift — Fully occupied | Construction | UPLIFT_PCT | 0.3 | q3_6_occupation=Fully occupied | Access mgmt, phasing, noise/dust, supervision. v4.5: not stacked with PH-1 — the higher of the two applies.
OCC-2 | Occupation uplift — Partially occupied | Construction | UPLIFT_PCT | 0.2 | q3_6_occupation=Partially occupied | Partial decant / zoned works. v4.5: not stacked with PH-1 — the higher of the two applies.
OCC-3 | Occupation uplift — Decant / Vacant | Construction | UPLIFT_PCT | 0 | q3_6_occupation=Full decant OR Currently vacant | No uplift.
PH-1 | Phasing uplift — multiple phases | Construction | UPLIFT_PCT | 0.15 | q4_6_phasing=Multiple phases | Sequential handovers extend site duration. v4.5 (Oct 2026): when occupation (OCC-1/OCC-2) also applies, only the HIGHER of the two is used — they no longer multiply. Lakeside (occupied, 6 sections, 45 wks) ran about 10% slower than Riley Court vacant.
FN-1 | Funding governance allowance — grant/public | Procurement/Pre-start | UPLIFT_WKS_RANGE | 4-8 | q4_7_funding=Grant or public funding | Approval governance before commitment. Add procurement compliance note.
DL-1 | Hard deadline | None (risk only) | RISK | 0 | q4_1 fixed/hard deadline | No duration change; adds Risk (E) +1% (NRM1) and a programme risk-register entry.
ACC-1 | Access uplift — low impact | Construction | UPLIFT_PCT | 0.1 | q3_5 includes Restricted working hours OR Access routes shared OR Tight site OR Site fronts a public road (old labels: Restricted hours, Shared access, Height/weight limits, Scaffold licence) | Site-logistics drag. Apply highest applicable ACC tier only (do not stack ACC-1+ACC-2). Cost side already in Prelims A (NRM1 Tab 3). Each selected constraint also seeds a LOW–MEDIUM risk-register entry — see risk map.
ACC-2 | Access uplift — high impact | Construction | UPLIFT_PCT | 0.175 | q3_5 includes Restricted deliveries or no vehicle access | Major access restriction. Apply the highest ACC tier only. Since v4.6, works limited to certain periods (Q3.5 + Q3.5a) take no uplift: the construction is fitted into the allowed windows instead (HOL rows below for school holidays).
PROG-FLOAT | Programme float / contingency | Total critical path | UPLIFT_PCT_RULE | +1 wk per 13 wks | Always | Report a best-case (no float) and a realistic (with float) date. Increase float when risk register is heavy.
HOL-1 | School holiday — summer | Construction window | WINDOW | 07-22/09-01 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).
HOL-2 | School holiday — Christmas | Construction window | WINDOW | 12-20/01-03 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).
HOL-3 | School holiday — Easter (moves each year; check the dates) | Construction window | WINDOW | 03-29/04-12 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).
HOL-4 | School holiday — October half-term | Construction window | WINDOW | 10-24/11-01 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).
HOL-5 | School holiday — February half-term | Construction window | WINDOW | 02-13/02-21 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).
HOL-6 | School holiday — May half-term | Construction window | WINDOW | 05-23/05-31 | q3_5a_workWindow = School / university holidays only | MM-DD/MM-DD, typical England school holidays. Construction weeks are fitted into these windows; a week counts when its middle day falls inside one. Added v4.6 (Oct 2026).

## FastTrack
LeverID | Lever — facilitate / skip pre-construction work | Trigger (when offered) | Action on programme | Approx weeks saved | Trade-off / risk to flag in report
FT1 | Start point = design stage already reached | q4_5_designStage past Stage 1 | Remove completed design stages (Stage 2 and/or 3 and/or 4) from the critical path; programme starts at the next stage. | 6 – 30 | None — reflects work already done. Confirm the existing design is sound and reusable.
FT2 | Reuse existing surveys / reports | q3_3_surveys lists a matching survey | Remove the matching survey row (SV1-SV6). Reduce Risk (E) allowance (NRM1). | 0 on critical path; de-risks | Survey must be current and scope-relevant. Asbestos register must be a valid R&D survey to drop SV2.
FT3 | At-risk design overlap | q4_4_priorities includes Speed AND planning required | Allow Stage 4 / tender prep to start before planning is granted — do not carry the full planning wait on the critical path. | 4 – 8 | Abortive design/tender cost if consent is refused or conditioned. Client must accept the risk in writing.
FT4 | Framework / call-off procurement | q4_4_priorities includes Speed; or client has a framework | Replace TN1 Formal Competitive (10-14) with TN3 Framework (3-6). | 6 – 10 | Framework rates may be higher than open tender. Must be a compliant pre-procured framework.
FT5 | RBCA instead of LABC | q4_4_priorities includes Speed | Replace BC1 LABC with BC2 RBCA (parallel, faster). | 0 – 4 (when BC is critical) | Not permitted for Higher-Risk Buildings (BSR Gateway 2). Private-sector fee.
FT6 | Early enabling / demolition package | demolition/strip-out in q2_2 AND speed | Move CD1 Demolition/Enabling off the main critical path to run during design (separate early contract). | CD1 duration (1-18) | Two-contract interface risk; needs early design freeze of the strip-out scope and asbestos clearance first.
FT7 | Long-lead procurement of major plant | 4+ M&E systems OR specialist plant in q2_2 | Order switchgear / AHUs / lifts during design (advance payment / client free-issue). | 8 – 30 (off critical path) | Commits spend before contract award; specification must be fixed early. Flag plant lead times to the client.
FT8 | Delegated authority / merged gateways | q4_4_priorities includes Speed | Reduce GW and GW3 from 2 wks to 1 wk, or merge Stage 2/3 reviews. | 1 – 3 | Requires pre-agreed delegated sign-off; less senior scrutiny at each stage.
FT9 | Permitted Development route | q3_4=Permitted development | Use PL0 (0 wks) instead of full planning (8-13). | 8 – 13 | Confirm PD rights with the LPA; prior-approval notification may still apply. University/Crown land rules vary.
FT10 | Two-stage tender with PCSA | q4_4_priorities includes Speed AND Design quality | Appoint contractor early under PCSA; overlap tender 2 with Stage 4. | 4 – 8 | Less price certainty at appointment; second-stage price risk. Good where buildability input is valued.

## Assumptions
Code | Assumption Text
A1 | Programme durations are indicative only and based on information provided at RIBA Stage 0-1. Actual durations to be confirmed at Stage 2 once surveys, design scope and procurement strategy are finalised.
A2 | Durations assume client decision-making within the gateway periods shown. Delays to client sign-off will extend the programme accordingly.
A3 | Planning determination periods are based on statutory LPA timescales. No allowance has been made for objections, committee referral or appeals.
A4 | Building control: LABC Full Plans assumed (parallel with Stage 4). A private RBCA (3-5 wks) should be considered for programme-critical projects — decision by the PM at Stage 2. Higher-Risk Buildings require BSR Gateway 2 and are out of scope of this reference.
A5 | Construction duration is benchmarked against project size and type at standard productivity. Actual duration to be confirmed at Stage 2 by the appointed contractor or QS.
A6 | Where the building is occupied during works, a construction uplift is applied (Modifiers OCC) for access management, phasing, noise/dust control and increased supervision.
A7 | Surveys identified as required but not yet commissioned are shown in parallel with early design and do not extend the critical path — except an asbestos R&D survey where intrusive/strip-out works are in scope, which must precede design freeze.
A8 | The programme does not show calendar dates. Durations are weeks from a notional start (Week 0 = Gateway 1 approval). Allow separately for holiday shutdowns when converting to dates.
A9 | Procurement threshold applied is the client's internal governance threshold (£100,000), not the statutory public-procurement threshold. Formal competitive tender 10-14 wks; three quotations 3-6 wks; framework call-off 3-6 wks.
A10 | Handover (RIBA Stage 6) includes commissioning, snagging and Practical Completion sign-off. The defects liability period begins at Practical Completion and is typically 12 months.
A11 | Where the client elects to facilitate or compress the programme (FastTrack levers), the associated trade-off or risk is stated in the report. At-risk overlap (FT3) and early procurement (FT6/FT7) commit cost ahead of approvals.
A12 | A programme float (Modifiers PROG-FLOAT) is added to give a realistic completion date alongside the best-case date. Float increases with the weight of the risk register.